## Master Timeline
Categories | Task | Notes | Date Due | Hours | Owner | Parent
Meetings/Planning | Misc Planning and Documentation | ~10% of allocated time | 2025-01-01 | 18 | Data
Meetings/Planning | Facilitate Working Group Jan |  | 2025-01-08 | 1.5 | Data
Meetings/Planning | Internal DD team meetings Jan | 1 hour * 5 people | 2025-01-14 | 5 | Data; CE; Events
Meetings/Planning | RDR Q1 |  | 2025-01-29 | 2 | Data
Meetings/Planning | Facilitate Working Group March |  | 2025-03-12 | 1.5 | Data
Meetings/Planning | Internal DD team meetings Mar | 1 hour * 5 people | 2025-03-12 | 5 | Data; CE; Events
Meetings/Planning | Facilitate Working Group April |  | 2025-04-09 | 1.5 | Data
Meetings/Planning | RDR Q2 |  | 2025-04-30 | 2 | Data
Logistics | FInalize Venue |  | 2025-04-30 | 3 | Events; Data
Meetings/Planning | Facilitate Working Group May |  | 2025-05-14 | 1.5 | Data
Meetings/Planning | Internal DD team meetings May | 1 hour * 5 people | 2025-05-14 | 5 | Data; CE; Events
Meetings/Planning | Facilitate Working Group June |  | 2025-06-11 | 1.5 | Data
Meetings/Planning | Facilitate Working Group July |  | 2025-07-09 | 1.5 | Data
Meetings/Planning | Internal DD team meetings Jul | 1 hour * 5 people | 2025-07-09 | 5 | Data; CE; Events
Meetings/Planning | RDR Q3 |  | 2025-07-30 | 2 | Data
Meetings/Planning | Facilitate Working Group Aug |  | 2025-08-13 | 1.5 | Data
Programming | Select Theme |  | 2025-08-31 | 2 | Data
Keynotes | 1. Recruit Keynotes | 1. Active Emailing 2. Meeting in-person 3. Initial Zoom Meeting | 2025-09-01 | 20 | Data
Sponsors | Update/Finalize sponsorship package |  | 2025-09-01 | 2 | Events; Data
Sponsors | Recruit sponsors |  | 2025-09-01 | 20 | Data
Sponsors | Design sponsorship brochure |  | 2025-09-01 | ? | CE
Sponsors | Update Sponsorship website section |  | 2025-09-01 | ? | CE
Meetings/Planning | Facilitate Working Group Sep |  | 2025-09-10 | 1.5 | Data
Meetings/Planning | Internal DD team meetings Sep | 1 hour * 5 people | 2025-09-10 | 5 | Data; CE; Events
Sessions | Update/Finalize call for session proposals |  | 2025-09-14 | 4 | Data
Sessions | Promote call for session proposals | This will generally be announced at the Summit on Sustainability. | 2025-09-30 | 20 | Data
Sessions | Update website with CFP |  | 2025-09-30 | ? | CE
Sessions | Convert CFP to online form |  | 2025-09-30 | 2 | Data
Sessions | Design CFP Promotion Slide |  | 2025-09-30 | 2 | CE; Data
Sessions | Update CFP Website section |  | 2025-09-30 | ? | CE
Sessions | Email call for session proposals |  | 2025-10-01 | 6 | Data
Meetings/Planning | Facilitate Working Group Oct |  | 2025-10-08 | 1.5 | Data
Meetings/Planning | RDR Q4 |  | 2025-10-29 | 2 | Data
Registration | Open registration |  | 2025-11-01 | ? | Events
Registration | Update website with registration |  | 2025-11-01 | ? | CE
Registration | Eventbright site |  | 2025-11-01 | ? | Events
Meetings/Planning | Facilitate Working Group Nov |  | 2025-11-12 | 1.5 | Data
Meetings/Planning | Internal DD team meetings Nov | 1 hour * 5 people | 2025-11-05 | 5 | Data; CE; Events
Keynotes | 2. Finalize keynotes |  | 2025-11-14 | 5 | Data
Keynotes | 3. Get Keynote Bios and headshots |  | 2025-11-14 | 1 | Data
Sessions | Close call for session proposals |  | 2025-11-14 | 1 | Data
Sessions | Select sessions |  | 2025-11-30 | 8 | Data
Sessions | Confirm selected session speakers |  | 2025-12-07 | 3 | Data
Meetings/Planning | Facilitate Working Group Dec |  | 2025-12-10 | 1.5 | Data
Programming | Establish Tracks |  | 2025-12-31 | 6 | Data
Programming | Finalize agenda |  | 2025-12-31 | 6 | Data
Sessions | Session list/schedule |  | 2025-12-31 | 4 | Data
Sponsors | Sponsorship confirmation |  | 2025-12-31 | ? | Events
Programming | Update website with agenda |  | 2026-01-07 | ? | CE
Keynotes | 4. Communication Final Details | 1. Confirm topic and Session 2. Send Question if panel 3. Get Slides | 2026-01-10 | 4 | Data
Sessions | Collect session slide decks |  | 2026-01-14 | 5 | Data
Programming | Design/Print Brochures |  | 2026-01-30 | ? | CE
Registration | Close registation |  | 2026-01-30 | ? | Events
Sessions | Upload slide decks to laptops |  | 2026-01-30 | 3 | Data
Logistics | Event Signage |  | 2026-02-01 | ? | CE
Registration | Final Attendee email |  | 2026-02-04 | 1 | Events
Programming | Send final instructions to attendees |  | 2026-02-05 | ? | Events
Logistics | Slides for breaks |  | 2026-02-07 | 2 | CE; Data
Logistics | Slides for introducing sessions |  | 2026-02-07 | 2 | CE; Data
Logistics | Slides for introducing keynotes |  | 2026-02-07 | 2 | CE; Data
Logistics | Laptops for session rooms | Loaded with slides | 2026-02-08 | 3 | IT; Data
Logistics | Set up registration | Name Tags? | 2026-02-10 | ? | Events
Sponsors | Invoice Sponsors |  | 2026-02-10 | ? | Events
Logistics | Finalize catering |  | ? | ? | Events

## Time Allocations
Owner | Sum of Hours
Data | 161
Data; CE; Events | 30
CE; Data | 8
Events; Data | 5
IT; Data | 3
Events | 1
CE | 0
Grand Total | 208

## Task Categories
Programming
Logistics
Sessions
Keynotes
Sponsors
Registration
Meetings/Planning